## Group member 1
To-do list
To be completed by: |  | Group Leader |  | Azmain Abrar
Deadline: |  | 2025-12-16 |  | Database Design and Implementation(Last Project)
Last Project
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Read Textbook | 2025-12-01 | 2025-12-07 | 2025-12-09 | 8 days | Go over resources to make notes
100% | Gather Information | 2025-12-03 | 2025-12-07 | 2025-12-09 | 6 days | issues with undertanding concepts
100% | Meeting 1 | 2025-12-04 | 2025-12-04 | 2025-12-04 | 1 day | remind group leader of tasks due
100% | Repo Creation | 2025-12-07 | 2025-12-07 | 2025-12-07 | 1 day | completed
100% | Tables & Data Type Creation | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2 days | completed
100% | Meeting 2 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 1 day | Prep for group video discussion. Account for emergency delays
100% | Presentation Slides | 2025-12-12 | 2025-12-14 | 2025-12-15 | 3 days | powerpoint slides error checks
100% | Group Recording | 2025-12-13 | 2025-12-13 | 2025-12-13 | 1 day | Final group video
100% | Follow-up Meeting | 2025-12-13 | 2025-12-13 | 2025-12-13 | 1 day | Check repo has all required files. Brightspace submission.

## Group member 2
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 3
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 4
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 5
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 6
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up